## Sheet1
Tasks | Estemated time (hr) | Actual Time (hr) | % complete
project setup | 2 | 2 | 100%
cofigure selenium and chrome driver for local-development | 1 | 1 | 100%
make an automation implementation for one supported retailer | 2
make an automation implementation for the remaining three supported retailers | 3
send email to owner | 2
implement selenium to run chrome simultaneously in new tab for all retailers | 2
implement chrome for production | 2
deploy the project to Heroku | 1.5
Documentation with all the steps | 4
Misc. | 3
Total | 22.5